## Foglio1
WBS (Task) | Name | POA | BCWS | ACWP | progr. ( PM appr.) | BCWP | CPI | SPI | CV | SV | TIME (IN m) | PEOPLE | Hourly rate | Cost per day
PDK 008 | BAP002 for Company A | 1080.62 | 718 | 730 |  | 722.67 | 0.98996 | 1.0065 | -7.33 | 4.67 |  |  | (160 h/m)
WP1 | Productiom of BP002 | 679.8 | 669.4 | 673 |  | 670.84 | 0.99679 | 1.0022 | -2.16 | 1.44
WP1.1 | Detailed Spec | 11.2 | 11.2 | 12 | 100% | 11.2 | 0.93333 | 1 | -0.8 | 0 | 0.5 | 2 | 70 | 150
WP1.2 | Customization | 11.2 | 11.2 | 12 | 100% | 11.2 | 0.93333 | 1 | -0.8 | 0 | 0.5 | 2
WP1.3 | Manufacture | 540 | 540 | 540 | cost-to-cost | 540 | 1 | 1 | 0 | 0
WP1.4 | Buy Compressor | 15 | 15 | 15 | cost-to-cost | 15 | 1 | 1 | 0 | 0
WP1.5 | Inside Integration & Test | 22.4 | 12 | 14 | 60% | 13.44 | 0.96 | 1.12 | -0.56 | 1.44 | 1 | 2
WP1.6 | Spare parts kit | 80 | 80 | 80 | cost-to-cost | 80 | 1 | 1 | 0 | 0
WP2 | Site Design | 41.2 | 8.6 | 12 |  | 7.28 | 0.60667 | 0.84651 | -4.72 | -1.32
WP2.1 | Layout Design | 5.6 | 5.6 | 6 | 100% | 5.6 | 0.93333 | 1 | -0.4 | 0 | 0.5 | 1
WP2.2 | Electric Panel (buy) | 30 | 0 | 0 |  | 0 |  |  |  | 0
WP2.3 | Network Design | 5.6 | 3 | 6 | 30% | 1.68 | 0.28 | -1.32 | -4.32 | -2.72 | 0.5 | 1
WP3 | Manuals and Training | 31.2 | 0 | 0 |  | 0
WP3.1 | Manuals production | 20 | 0 | 0 | 0% | 0
WP3.2 | Training set up | 11.2 | 0 | 0 | 0% | 0 |  |  |  |  | 1 | 1
WP4 | On Site Activities | 82.2 | 0
WP4.1 | Shipment | 10 |  |  | cost-to-cost
WP4.2 | Site Set up | 7.1 | [8 empty] | 0.25 | 2 |  | 10d
WP4.3 | Equipment installation | 31.4 | [8 empty] | 1 | 2 |  | 60d | 9000
WP4.4 | Commissioning | 10.9 | [8 empty] | 0.75 | 2 |  | 15d | 2250
WP4.5 | Acceptance test | 7.1 | [8 empty] | 0.25 | 2 |  | 10d
WP4.6 | Support to Start | 15.7 | [8 empty] | 1 | 1 |  | 30d
WP5 | Training | 11.22 | 0
WP5.1 | Training for operators | 2.06
WP5.2 | Training for Supervisors | 2.06
WP5.3 | Training for Technicians | 7.1
WP6 | Warranty | 100 | 0
WP6.1 | Warranty period | 100
WP7 | Project management | 135 | 40 | 45 | 33% | 44.55
WP7.1 | Risk Contingencies | 50 | 0
WP7.2 | Management and Control | 85 | 40