## Foglio1
WBS (Task) | Name
PDK 008 | BAP002 for Company A
WP1 | Production of BP002
WP1.1 | Detailed Spec
WP1.2 | Customization
WP1.3 | Manufacture
WP1.4 | Buy Compressor
WP1.5 | Inside Integration & Test
WP1.6 | Spare parts kit
WP2 | Site Design
WP2.1 | Layout Design
WP2.2 | Electric Panel (buy)
WP2.3 | Network Design
WP3 | Manuals and Training
WP3.1 | Manuals production
WP3.2 | Training set up
WP4 | On Site Activities
WP4.1 | Shipment
WP4.2 | Site Set up
WP4.3 | Equipment installation
WP4.4 | Commissioning
WP4.5 | Acceptance test
WP4.6 | Support to Start
WP5 | Training
WP5.1 | Training for operators
WP5.2 | Training for Supervisors
WP5.3 | Training for Technicians
WP6 | Warranty
WP6.1 | Warranty period
WP7 | Project management
WP7.1 | Risk Contingencies
WP7.2 | Management and Control