## Slide 1: Kick off Meeting
BAP002
Magistrello Camilla

## Slide 2: Agenda
ATTENDEES
INTRODUCTION TO THE PROJECT
OBJECTIVES
ROLES AND RESPONSIBILITIES
TIMELINE
Q&A
RISK CLASS
COST & EVA

## Slide 3: ATTENDEES
Paolo: Project Manager
Laura: Engineering
Leonardo: On Site Activities
Giorgio: Quality
Carlo: Training
Pasquale: Purchasing
Gianni: Manufacture
Paola: Configuration Management
Giada: Manuals
Marcello: Logistics
Marco: Installation

## Slide 4: OBJECTIVES
The main objective is the turnkey delivery of an equipment for the automated packaging of bottles, BAP002, including compressor.
A spare parts kit for the warranty period (one year).

## Slide 5: OBJECTIVES
Training in class and on the job for
  Up to 10 operators: one session of 5 hours (one day)
  Up to 3 supervisors: one session of 12 hours (two days)
  Up to 4 maintenance technicians: one session of 24 hours (four days)
A complete set of manuals: Technical, Maintenance, Troubleshooting in electronic format (3 copies of each manual).

## Slide 6: OBJECTIVES
A complete system capable of:
Feed bottles one by one from a pallet to the packaging equipment
Move the bottles to the packaging station
Pack the bottles in cardboard box: the number of bottles per box shall be selected from a fixed and predetermined options list
Send the box to the palletizing machine (not included in the delivery)
Characteristics

## Slide 7: OBJECTIVES
The system is engineered to accommodate bottles of various sizes, including 200ml, 750ml, and 1000ml.
Is designed to achieve the following throughput rates:
200ml bottles: Capable of processing up to 1,000 bottles per hour.
750ml bottles: Handles up to 600 bottles per hour.
1000ml bottles: Efficiently manages up to 400 bottles per hour.
Features

## Slide 8: OBJECTIVES
The Customer will provide the following:
Area: A flat space measuring 20x50 meters, with lighting at 300 lux/m².
Electrical Supply: A main electrical line with a capacity of 75 KVA and 380 V ± 7%, suitable for powering both the BAP002 system and the compressor.
Site

## Slide 9: ROLES AND RESPONSIBILITIES
Project Manager (Paolo): leads the project team, coordinates activities, and serves as the main point of contact for the client company.
Engineering (Laura): responsible for the technical and engineering aspects of the project.
On Site Activities (Leonardo): managing all on-site activities related to the project, coordinates the work at the project location.
Quality (Giorgio): ensuring that all project deliverables meet the highest quality standards.

## Slide 10: ROLES AND RESPONSIBILITIES
Training (Carlo): organizes and conducts training sessions for the client company's staff.
Purchasing (Pasquale): handles supplier selection, order issuance, and procurement management.
Manufacture (Gianni): oversees the production process and ensures that the equipment is made according to specifications.
Configuration Management (Paola): manages changes and configuration of the equipment, ensuring that all modifications are properly documented and implemented.

## Slide 11: ROLES AND RESPONSIBILITIES
Manuals (Giada): responsible for producing and customizing the technical manuals required for the operation and maintenance of the plant.
Logistics (Marcello): manages shipping and site logistics, ensuring that the equipment arrives on time and that the site is prepared for installation.
Installation (Marco): assists with the installation of the equipment and supports on-site activities, working closely with Leonardo to ensure effective commissioning.

## Slide 12: TIMELINE
Project Start: The project will officially begin with the signing of the contract.
Equipment Delivery (12 months): includes transportation and making the equipment available for installation.
Installation (14 months): includes the setup and initial testing of the plant.
Acceptance Testing (15 months): this phase will ensure that the equipment operates according to the agreed-upon specifications and meets the buyer's requirements.
Warranty Period (up to 27 months): assistance and support will be provided for any technical or maintenance issues according to the established terms.

## Slide 13: RISK CLASS: B
Geographical distribution of facilities/services (1 for headquarters in Genoa, 2 Italy, 3 EU, 4 Europe, 5 outside Europe, 0 for company initiatives) | 2
Participation in complex Consortia or RTI / subcontractors (A value from 1 to 5 will be assigned depending on the number of actors, the role, the company's position as leader or partner, etc.) | 0
Complexity (of the process to manage, the product/system to provide, the service to deliver) (1 simple, 2 medium, 3 complex, 4 very complex) | 2
Experience with the type of project (1 = already successfully done several times, 2 done several times with some issues, 3 done several times with different issues, 4 done a few times, 5 first time) | 2
Economic Value of the project (1<50K €, 2 between 50K € and 500K €, 3 between 500 and 2500K €, 4 between 2500 and 5000K €, 5 > 5000K €) | 3
Project margin (1 > 50%, 2 between 30% and 50%, 3 between 20% and 30%, 4 between 5% and 20%, 5 < 5%) | 3
Relevance of the project for the client (1 = not relevant, 2 relevant, 3 business critical, 4 life critical) | 3
Importance of the client (A value from 1 to 5 will be given depending on the strategic importance of the client) | 3
Total | 18

## Slide 14: COST & EVA
Total price (All-inclusive): 1.450.000€
Payments:
  20% at the order
  20% at the delivery on site
  20% at the end of installation
  40% at the final acceptance
Planned budget: 1.080.000,62€
Estimated Margins: Approximately €370,000
Markup: 0,34

## Slide 15: Q&A?

## Slide 16: GOOD LUCK