## IT Management
Task # | Task name | Start date | End date | BCWS | Cost distribution | Task Progress % (per month) | BCWP at control date | ACWP at control date
1 | Project setup & API key removal | start month 1 | end month 1 | 500 | linear
2 | UI scaffolding & bottom bar customization | start month 1 | end month 2 | 1000 | linear
3 | User authentication & password recovery | start month 2 | end month 2 | 700 | linear
4 | Profile management & camera integration | start month 2 | end month 3 | 1500 | linear
5 | Product catalog & product info display | start month 3 | end month 4 | 2000 | linear
6 | Shopping cart & booking system | start month 4 | end month 4 | 800 | linear
7 | Payment integration & order processing | start month 4 | end month 5 | 1200 | linear
8 | Admin module & order status management | start month 5 | end month 5 | 300 | linear
9 | Notifications & reviews system | start month 5 | end month 6 | 500 | linear
10 | Testing & continuous integration | start month 6 | end month 6 | 0 | linear

## Summary
Total Budget (€) | Customer Price (€) | Margin (%)
8500 | 10625 | 20